## Dashboard
MedSync — Implementation Tracker
Auto-updating rollup — edit Status in the Frontend / Backend sheets
Track | Total Tasks | Not Started | In Progress | Blocked | Done
Frontend | -423 | 38 | 0 | 0 | 0
Backend | -405 | 47 | 0 | 0 | 0
Total | -828 | 85 | 0 | 0 | 0
% Complete | -0%
Other Sheets
Security & Compliance Checklist
Production Extensions (Backlog)

## Frontend
Task | Sub-Module | Priority | Status | Owner | PRD Section | Notes / Blockers
Patient App
Registration / login screens | Patient App | P0 | Not Started |  | 4.1 / 28
Profile & identity information management | Patient App | P1 | Not Started |  | 3.1
Document upload flow (PDF / image, multi-file) | Patient App | P0 | Not Started |  | 4.2 / 28
Upload progress & processing-status indicators | Patient App | P1 | Not Started |  | 4.2
Extracted-information review & verify/correct UI | Patient App | P0 | Not Started |  | 4.3 / 28
Medical timeline view with type & date-range filters | Patient App | P0 | Not Started |  | 5 / 28
Timeline event detail + original source document viewer | Patient App | P1 | Not Started |  | 5
Clinical summary view (labeled AI-assisted) | Patient App | P2 | Not Started |  | 6
Emergency profile configuration UI | Patient App | P0 | Not Started |  | 7 / 28
Emergency contacts management (add/verify/priority) | Patient App | P0 | Not Started |  | 10.2 / 22 / 28
Emergency trigger enable/disable settings | Patient App | P1 | Not Started |  | 9
Manual SOS button + confirmation flow | Patient App | P0 | Not Started |  | 9.1 / 12 / 28
Emergency QR / identifier display | Patient App | P0 | Not Started |  | 8.1 / 28
Location permission prompt & sharing status UI | Patient App | P0 | Not Started |  | 11 / 28
Consent & access-history viewer | Patient App | P1 | Not Started |  | 14 / 30
Emergency event & notification history view | Patient App | P1 | Not Started |  | 3.1
Doctor Portal
Clinician login / MFA screen | Doctor Portal | P0 | Not Started |  | 4.1
Patient search / lookup with authorization gate | Doctor Portal | P0 | Not Started |  | 3.2 / 28
Structured medical history view | Doctor Portal | P0 | Not Started |  | 4.4 / 28
Longitudinal timeline view (clinician-facing) | Doctor Portal | P0 | Not Started |  | 5 / 28
Original source document viewer | Doctor Portal | P1 | Not Started |  | 3.2 / 28
Add / update clinical event form | Doctor Portal | P0 | Not Started |  | 3.2 / 28
AI-extracted information review UI | Doctor Portal | P1 | Not Started |  | 4.3
Clinical summary generation & display | Doctor Portal | P2 | Not Started |  | 6
Paramedic App
Responder login / verification screen | Paramedic App | P0 | Not Started |  | 3.3 / 28
Emergency identifier scan / lookup flow | Paramedic App | P0 | Not Started |  | 8.1 / 28
Emergency profile display (critical info prioritized) | Paramedic App | P0 | Not Started |  | 7 / 28
Break-glass access request + reason capture UI | Paramedic App | P1 | Not Started |  | 8.2
Request additional information flow | Paramedic App | P2 | Not Started |  | 3.3
Emergency access audit visibility for responder | Paramedic App | P2 | Not Started |  | 3.3
Admin Console
System configuration screens | Admin Console | P2 | Not Started |  | 3.5
Organization & role management UI | Admin Console | P2 | Not Started |  | 3.5
System health monitoring dashboard | Admin Console | P2 | Not Started |  | 3.5 / 26
Security / audit event review UI | Admin Console | P1 | Not Started |  | 3.5 / 15.3
Shared / Design System
Core design system & component library | Shared | P0 | Not Started |  | —
Accessibility & responsive layout pass | Shared | P1 | Not Started |  | —
Critical-alert visual prioritization pattern | Shared | P0 | Not Started |  | 7
Failure / degraded-state UI (GPS off, offline, stale data) | Shared | P1 | Not Started |  | 25

## Backend
Task | Sub-Module | Priority | Status | Owner | PRD Section | Notes / Blockers
Auth & Identity
Registration / login API | Auth | P0 | Not Started |  | 4.1 / 28
MFA for privileged roles | Auth | P0 | Not Started |  | 4.1
RBAC engine + resource-level authorization | Auth | P0 | Not Started |  | 15.2 / 28
Session & device management | Auth | P1 | Not Started |  | 4.1
Account recovery flow | Auth | P1 | Not Started |  | 4.1
Patient identity matching before record attach | Auth | P0 | Not Started |  | 4.1
Document Ingestion
Upload API + virus/malware scanning | Ingestion | P0 | Not Started |  | 4.2 / 15.1 / 28
Document classification service | Ingestion | P1 | Not Started |  | 4.2
OCR pipeline integration | Ingestion | P0 | Not Started |  | 4.2 / 28 / 30
Text normalization step | Ingestion | P1 | Not Started |  | 4.2
Object storage for original documents | Ingestion | P0 | Not Started |  | 4.2 / 19 / 30
AI Extraction
Medical entity extraction service | AI | P0 | Not Started |  | 4.3 / 28 / 30
Field normalization | AI | P1 | Not Started |  | 4.3
Confidence scoring | AI | P1 | Not Started |  | 4.3 / 30
Verification-state workflow (no silent overwrite) | AI | P0 | Not Started |  | 4.3 / 20
Source-linked extraction metadata (doc/page/timestamp/model) | AI | P0 | Not Started |  | 4.3 / 30
Medical Record & Timeline
Structured record schema (conditions, meds, allergies, etc.) | Records | P0 | Not Started |  | 4.4 / 16
Timeline generation / indexing service | Records | P0 | Not Started |  | 5 / 28
Timeline filter & query API (type, date range) | Records | P1 | Not Started |  | 5
Clinical summary generation service (source-grounded) | Records | P2 | Not Started |  | 6 / 28
Emergency Event Service
Emergency event state machine | Emergency | P0 | Not Started |  | 12
Manual SOS trigger API | Emergency | P0 | Not Started |  | 9.1 / 28 / 30
Device / external emergency trigger intake API | Emergency | P2 | Not Started |  | 9.1
Confirmation-window / false-positive handling logic | Emergency | P1 | Not Started |  | 24
Break-glass access workflow + reason logging | Emergency | P1 | Not Started |  | 8.2 / 30
Location Service
Location capture API | Location | P0 | Not Started |  | 11 / 28 / 30
Location encryption + configurable retention | Location | P0 | Not Started |  | 11
Graceful degradation (no fabricated location) | Location | P1 | Not Started |  | 11 / 25
Notification Service
Async notification dispatch (SMS / Push / Email) | Notification | P0 | Not Started |  | 10.1 / 21 / 28 / 30
Delivery status tracking | Notification | P1 | Not Started |  | 10.2
Duplicate-notification suppression per event | Notification | P1 | Not Started |  | 10.2 / 24
Emergency contact CRUD API | Notification | P0 | Not Started |  | 22 / 28
Consent & Permission
Consent / permission model & API | Consent | P0 | Not Started |  | 14
Permission revocation logic | Consent | P1 | Not Started |  | 14
Security & Audit
Encryption in transit & at rest | Security | P0 | Not Started |  | 15.1 / 30
Password hashing / secret management | Security | P0 | Not Started |  | 15.1
Server-side authorization enforcement on all endpoints | Security | P0 | Not Started |  | 15.2 / 30
Tamper-resistant audit logging service | Security | P0 | Not Started |  | 15.3 / 30
Rate limiting & common attack protections | Security | P1 | Not Started |  | 15.1
Data & API Layer
PostgreSQL schema implementation per data model | Data/API | P0 | Not Started |  | 16
Redis session / cache layer | Data/API | P1 | Not Started |  | 19
REST API implementation (full endpoint set) | Data/API | P0 | Not Started |  | 17
FHIR resource mapping (Patient, Condition, etc.) | Data/API | P2 | Not Started |  | 18
Infra & Observability
Async task queues (OCR, extraction, notifications) | Infra | P0 | Not Started |  | 27
Independent service scaling setup | Infra | P2 | Not Started |  | 27
Observability / monitoring (latency, errors, failures) | Infra | P1 | Not Started |  | 26
Dedicated emergency-workflow alerting | Infra | P1 | Not Started |  | 26

## Security & Compliance
Acceptance Criterion (PRD §30) | Status | Notes
APIs enforce server-side authorization | Not Tested
Sensitive data encrypted in transit | Not Tested
Sensitive data encrypted at rest where applicable | Not Tested
Authentication tokens/sessions are protected | Not Tested
Access events are auditable | Not Tested
Public possession of an emergency QR does not expose the complete medical record | Not Tested
A PDF/image can be uploaded successfully | Not Tested
OCR can extract text from supported documents | Not Tested
Selected medical entities can be extracted | Not Tested
Each extracted entity has a source reference | Not Tested
A user can verify/edit extracted information | Not Tested
Verified information appears in the timeline | Not Tested
Original documents remain accessible to authorized users | Not Tested
A patient can configure emergency contacts | Not Tested
A patient can configure an emergency profile | Not Tested
Manual SOS can create an emergency event | Not Tested
System can capture device location when permission/connectivity allow | Not Tested
Configured contacts receive an emergency notification through implemented channel | Not Tested
Notification includes timestamp and location when available | Not Tested
Emergency responders can access emergency profile through authorized workflow | Not Tested
Emergency access is logged | Not Tested
Break-glass access, if implemented, records a reason | Not Tested
Unauthorized users cannot access medical information | Not Tested

## Production Extensions
Future Capability (PRD §29) | Priority (future)
Hospital information-system integrations
Laboratory integrations
Wearable/device integrations
Advanced accident/fall detection
More sophisticated emergency routing
Interoperable FHIR APIs
Digital identity integration
Advanced consent management
Multilingual medical-document processing
Offline emergency workflows
Regional/organization-specific emergency policies
Advanced clinical search
Medical-record deduplication
Cross-provider data reconciliation